PROGRESS REPORT: DATA MIGRATION & SYSTEM PREPARATION

Cooperativ e: STA ANA MULTIPURPOSE COOPERATIVE (SAMCO)
Prepared by: ALVIN PIQUERO IT
Reporting Period:  4-24-25
Migration Cut-off Date: December 31, 2025
Status: Ongoing – On Track

1. EXECUTIVE SUMMARY

Data migration activities are currently underway. Key accomplishments include extraction of account records from legacy files, assignment of account numbers to beneficiaries, and data entry of over 7,000 savings accounts. Loan data entry is in progress. Hardware canvassing for new PC and server has also commenced to support the upcoming iAccs2013 system implementation.

2. ACCOMPLISHED TASKS

| # | Task Description | Status | Details |
| --- | --- | --- | --- |
| 1 | Extracted accounts from old records (ACCOUNT FILES.xlsx) | ✅ Completed | Data extracted, but requires matching between Savings Deposit and CBU accounts |
| 2 | Account number reconciliation (Savings vs CBU) | 🔄 In Progress | Need to compare names and assign current account numbers where missing |
| 3 | Assigned account numbers to beneficiaries | ✅ Completed | Beneficiaries now have mapped account numbers |
| 4 | Data entry for total savings accounts (7,000+) | ✅ Completed | All 7,000+ savings accounts encoded |
| 5 | Data entry for existing loans | 🔄 Current Task | Loan records being entered; ongoing |
| 6 | Canvassing for new PC and server | 🔄 In Progress | Preparing hardware requirements for system implementation |

3. DETAILED ACCOMPLISHMENTS

3.1 Account Extraction & Reconciliation

- Source File: ACCOUNT FILES.xlsx (old records)

- Completed: Raw extraction of account data

- Pending: Matching Savings Deposit accounts with CBU (Share Capital Build-Up) accounts

- Action Required: Compare member names across both data sets and assign the correct current account number

3.2 Beneficiary Account Number Assignment

- Status: Complete

- Deliverable: All beneficiaries now have assigned account numbers for tracking

3.3 Savings Account Data Entry

- Volume: 7,000+ accounts

- Status: Fully encoded

- Remarks: This includes Regular Savings and potentially Special Savings (pending formula confirmation)

3.4 Loan Data Entry (Current)

- Volume: Being encoded

- Loan Types: Salary, Small Business, Honorarium, Emergency, Renewal

- Status: In progress – expected completion end of May 2026

3.5 Hardware Canvassing (Current)

- Objective: Prepare for iAccs2013 system implementation

- Items being canvassed:

  - New PC workstations (to replace outdated Pentium/2GB RAM units)

  - Dedicated server (currently none)

- Next Step: Submit quotation comparisons to SAMCO Management for approval

4. PENDING / NEXT STEPS

| Task | Priority | Responsible | Target Completion |
| --- | --- | --- | --- |
| Complete loan data entry | High | Alvin Piquero | End of May |
| Match Savings Deposit names to CBU accounts | High | Alvin Piquero | April 3, 2024 |
| Assign current account numbers to matched records | High | Alvin Piquero | April 3, 2024 |
| Finalize hardware canvassing (PC + server) | Medium | Alvin Piquero/ Admin | TBD |
| Submit hardware quotation to Management | Medium | Alvin Piquero | TBD |
| Begin data validation (SL vs GL reconciliation) | Medium | Bookkeeper | TBD |
| Finalize pending policies (loan, special savings) | Low | SAMCO Management | TBD |

5. CHALLENGES & CONCERNS

| Challenge | Impact | Suggested Resolution |
| --- | --- | --- |
| Matching Savings Deposit to CBU accounts is manual and time-consuming | Medium | Allocate dedicated staff; use Excel lookup functions |
| 7,000+ accounts already encoded but may contain inconsistencies | Medium | Run validation script or manual spot-check |
| Loan data entry volume unknown until completion | Low | Continue encoding; track progress daily |
| No approved budget yet for PC/server | High | Expedite canvassing and submit early for approval |

6. HARDWARE & SOFTWARE LICENSING COST ESTIMATION

To prepare for the successful implementation of the iAccs2013 system, the following hardware upgrades and software licensing are required. These estimates are based on current market rates for government and cooperative IT procurements in the Philippines.

6.1 Workstation PCs (2-3 Units)

The existing cashier and loan officer units with Pentium processors and 2-4GB RAM must be replaced to meet iAccs2013 compatibility requirements.

| Specification | Requirement | Notes |
| --- | --- | --- |
| Processor | 6+ Cores, up to 4.3GHz | I3 or I5 equivalent |
| RAM | 16GB DDR4 | Higher than minimum for future-proofing |
| Storage | 512GB NVMe SSD | Fast read/write for database operations |
| OS | Genuine Windows 11 Home (lifetime license) | Pre-installed with license |
| Monitor | 22" - 24" | Included in package |
| Peripherals | Wireless keyboard & mouse | Included |
| Warranty | 1 year parts and labor | Carry-in |

Estimated Cost per Unit: ₱27,500 - ₱45,000
Estimated Total for 3 Units: ₱82,500 - ₱135,000

*Note: Government procurement references show ₱27,500 for an all-in-one desktop with Windows 11 license, while higher-spec units with 32GB RAM reach ₱45,000.*

6.2 Dedicated Server (1 Unit)

| Specification | Requirement | Notes |
| --- | --- | --- |
| Processor | Intel Xeon or equivalent | Enterprise-grade |
| RAM | 32GB minimum | For multi-user concurrent access |
| Storage | RAID configuration | Redundancy for data protection |
| OS | Windows Server (license separate) | See licensing section |
| Network | Gigabit Ethernet | For LAN connectivity |
| Form Factor | Tower or Rack-mount | Based on office space |

A dedicated server is critical as SAMCO currently has no centralized server infrastructure. This will host the iAccs2013 database and manage network traffic.

Estimated Cost per Unit: ₱80,000 - ₱150,000

*Note: For smaller cooperatives, a high-end business PC spec (₱50,000-₱60,000) configured as a dedicated server may suffice initially, but an enterprise server is recommended for 7,000+ members.*

6.3 Passbook Printer (1 Unit)

To replace the manual typewriter currently used for passbook updates.

| Model | Estimated Price | Notes |
| --- | --- | --- |
| Epson PLQ-35 Passbook Printer | ₱33,000 - ₱38,000 | Specialized passbook printer, compatible with banking systems |
| Epson PLQ-20 (Alternative) | ₱7,600 - ₱8,000 | Older model, still available, lower cost option |

Recommended: Epson PLQ-35 (newer model, longer support)
Estimated Total: ₱33,000 - ₱38,000

6.4 Software Licensing

SAMCO currently runs unlicensed software, which poses legal and compliance risks. The following licenses are required for migration:

| Software | License Type | Estimated Cost | Notes |
| --- | --- | --- | --- |
| Windows Server 2022 Standard | Perpetual (16 core license) | ₱35,000 - ₱50,000 | For dedicated server |
| Windows 11 Pro (3 units) | OEM (per device) | ₱8,000 - ₱10,000 per unit | For new workstations (if not included) |
| Microsoft SQL Server Standard | Perpetual or Subscription | ₱60,000 - ₱120,000 (perpetual) OR ₱15,000 - ₱25,000/year (subscription) | Database backend for iAccs2013 |
| iAccs2013 Licensing | Cooperative Software License | To be confirmed with coreDev Solutions | The existing setup is unlicensed; management must regularize |
| Coopbase Solutions Alternative (if switching) | Community Edition (free) + Implementation Fee | Implementation: ₱50,000 - ₱150,000 (one-time) | Some cooperative software offers free licensing with paid implementation |

Estimated Software Licensing Total: ₱120,000 - ₱355,000 (one-time) + annual subscriptions where applicable

7. SUMMARY OF COST ESTIMATES

| Item | Quantity | Low Estimate (₱) |  | High Estimate (₱) |
| --- | --- | --- | --- | --- |
| Workstation PC (with OS license) | 3 units | 82,500 |  | 135,000 |
| Dedicated Server (hardware only) | 1 unit | 80,000 |  | 150,000 |
| Passbook Printer | 1 unit | 33,000 |  | 38,000 |
| Windows Server License | 1 unit | 35,000 |  | 50,000 |
| Windows 11 Pro (if not bundled) | 3 units | 24,000 |  | 30,000 |
| SQL Server License | 1 unit | 60,000 (just incase) |  | 120,000 (just incase) |
| SUBTOTAL (Hardware + Licensing) |  | ₱314,500 |  | ₱523,000 |
| Contingency (10-15%) |  | ₱31,450 |  | ₱78,450 |
| GRAND TOTAL ESTIMATE |  | ₱345,950 |  | ₱601,450 |

7. NEXT REPORTING DATE

- Next Progress Update: End of May

- Milestone Target: Completion of loan data entry + hardware approval

PREPARED BY:

ALVIN PIQUERO
IT/Encoder/Data Migration Lead
4-24-26